TAGRA(2012)05

TAGRA –2012/13 to 2013/14 work plan

# Introduction

This paper sets out TAGRA’s high level work plan between 2012/13 and 2013/14. The work plan is based on discussions at the April TAGRA meeting. The work plan should be read in conjunction with papers TAGRA(2012)06 (Remote & Rural subgroup objectives) and TAGRA(2012)07 (Morbidity and Life Circumstances objectives).

# BackgrounD

In April, TAGRA were asked to nominate the four developmental projects that they would like to see undertaken between 2012/13-2013/14. This is in addition to the full NRAC formula run in 2012/13.

PROPOSED WORK PLAN

The following TAGRA work plan has been agreed for 2012/13-2013/14:

Review of acute costs

GP out of hours and De Minimis work through the Remote & Rural subgroup

Review of MLC

Review of population estimates

Annual NRAC formula run

The following table outlines the resource estimates required to undertake the programme of work, timescales and project leads. Note, the work plan excludes resourcing  required for  routine NRAC work, for example, answering Parliamentary Questions, briefing, ad hoc queries which occur throughout the year.

| Project | Estimate of Analytical Support Team resource required | Estimate of wider resources required | Project timescales | Project lead | TAGRA representative | Progress – Green / Amber / Red | AST Risks | Countermeasure |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NRAC formula update | 45 days |  | May – August 2012 | Roger Black | Roger Black | GREEN | ISD staff changes | Flexible staffing to allow analysts previously involved in formula update to assist. |
| Remote & Rural | 80 days | HERU (Aberdeen University) | Full financial year 2012/13 | Jill Vickerman | Jill Vickerman | AMBER | AST Staff resources Assumes the analysis does not throw up unexpected findings which merit further investigation. | Subgroup meetings planned for September and January to check progress. |
| Morbidity & Life Circumstances (Mental Health & Learning Difficulties) | 140 days |  | Full financial year 2012/13 | Marion Bain | Marion Bain | AMBER | AST Staff resources Assumes the analysis does not throw up unexpected findings which merit further investigation. | Subgroup meetings planned for October and January/February to check progress. |
| Population estimates | 6 days | National Records of Scotland, NHS GG&C, City of Glasgow Council, NHS CR, ISD Scotland data linkage team | 2012/13-2013/14 | Kirsty MacLachlan | Paul James / Linda De Caestecker | GREEN |  |  |
| Acute costs review | 60 days |  | January - March 2013 | Roger Black | Roger Black | GREEN | New staff member | Support from current team |

Code to Risk:

Red – Significant risk to being delivered on time

Amber – Risk to elements of project not being delivered on time, or a small risk to the delivery of the project being late

Green – Project progressing to schedule

RISKS TO DELIVERY

These projects represent TAGRA Analytical Support Team’s ambitions for the coming two years in addition to the annual formula update. There is a risk that they cannot be delivered due to resource constraints but by building the work plan over two years means there is greater flexibility around when different work programmes can be taken forward.

Potential risks to any work plan are discussed below. These risks relate more to the GP out of hours and the population estimates work. The other proposed elements of the work plan are more self-contained pieces of work and it should be possible to provide firmer indications of requirements in terms of resources and timescales.

Required resources

Some of these projects, by their nature, are potentially open ended. Whilst the review of the acute costs is relatively well defined and a self-contained pieces of work, any review of GP out of hours, the MLC adjustment and the population estimates project, are potentially extremely lengthy pieces of work. It is difficult to specify the timescales and resources required to undertake this work thoroughly, as there is a risk that any initial review of the area identifies issues which are currently unknown, either requiring further detailed analysis or opening entirely new avenues of investigation. The population estimates project in addition will involve data sharing and therefore several data controller approval stages.

CONCLUSION

TAGRA members are invited to note the high level work plan. A further update will be available for December’s TAGRA meeting.

TAGRA Analytical Support Team (Health ASD & ISD)

August 2012

ANNEX A – Descriptions and resource requirements (Extract from Paper TAGRA(2012)04)

Full NRAC formula update

Priority =	High

Estimate of resource required

0.3 WTE.

3 year rolling programme for updating elements of the formula

Priority =	High		NRAC recommendation: 10.1

Description

NRAC recommended that the population, age-sex and some components of the excess costs elements of the formula should be updated annually. The remaining elements of the formula should be updated at a minimum every three years as part of a rolling programme of work to maintain the integrity of the formula.

The table below shows a proposal to maintain the formula using a three year rolling programme to update all relevant elements of the formula. 2012/13 is year 3 in the rolling programme.

| Formula element | To be updated | Proposed frequency of update | Amount of resource required |
| --- | --- | --- | --- |
| Age-sex | Fixed/variable cost split for acute age-sex cost weights | Year 2 | Moderate |
| MLC | Variables making up needs indices Coefficients measuring relationship between indices and costs | Year 1 Year 1 | Significant Significant |
| Hospital excess costs | Updating the classification of data zones to reflect changes in the Scottish Government Urban Rural Classfication. | Year 2 | Moderate |
| Community travel excess costs | Proportions of population within settlements of particular sizes Travel times to nearest settlements of particular sizes Average within-settlement travel times Base locations Island contact times | Year 3 Year 3 Year 3 Year 3 Year 3 | Moderate Moderate Moderate Moderate Moderate |

GP out of hours

Priority =	High		NRAC recommendation: n/a

Description

A separate GP out of hours care programme is not identified within the current formula. Improvements to the Costs Book mean that GP out of hours costs can now be separately identified, and improving information on activity increase the possibility that a separate adjustment could be made.

Estimate of resource required

High - First stage of work would be to explore the availability of cost and activity data by board, and the degree to which data is available by age and sex. Emerging data sets being collected by SG and ISD may be able to inform this analysis, but there is an associated risk that the data may prove inadequate for an adjustment to be made in the formula.

A second stage of work may be to consider the appropriateness of any proposed adjustment, and the fairness to NHS Boards of continuing to fund GP OOH services within the NRAC general allocation.

Significant resource required.

Feasibility

Depends on (a) specification of work and (b) availability of data

Update to MLC

Priority =	High		NRAC recommendation: 5.6

Description

TAGRA has indicated that it would like to review the MLC adjustment within the NRAC formula. There is no one MLC adjustment, rather, it consists of separate adjustments for each of the six care programmes. The acute care programme consists of seven separate adjustments at the level of diagnostic groups.

Updating all elements of the MLC would be an extremely resource intensive piece of work. ASD would recommend updating different the elements of the MLC in stages; this is the approach used to update the formula in England.

The Mental Health and Learning Difficulties adjustment was looked at last year but it will continue into 2012/13. Once this programme is completed, proposals will be brought to TAGRA to select another care programme to review.

Estimate of resource required

High – The update would involve re-estimating the MLC adjustment from scratch. TAGRA may wish to involve consultation with the NHS Boards to determine what indicators they would want to have considered for potential inclusion in any revised adjustment.

Significant resource required.

Feasibility

Depends on specification of work

Review of acute costs

Priority =	High		NRAC recommendation: 10.10

Description

Currently, acute activity is measured using episodes. Experience of the National Tariff is that, due to different service designs between and within boards, this can make board data difficult to compare. This lack of comparability between boards causes variability in the data, and means that it is difficult to determine whether differences between different areas are due to genuine differences in need or to different recording practices, which is the purpose of the NRAC formula. Having a more consistent measure of activity should improve the performance of the formula in the age-sex, MLC, and unavoidable excess cost adjustments. Also to consider the approach to costing (patient level) being developed as part of the Integrated Resources Framework project.

Estimate of resource required

High - First stage of work would be to scope the methodology by which cost and activity would be mapped to spells within specialty. Similar work has been undertaken as part of the National Tariff, and it should be possible to learn from this, but the NRAC formula requires data presented in a different format, so further work would likely be required.

Significant resource required.

Feasibility

Depends on specification of work

Population estimates

Priority =	High		NRAC recommendation: N/A

Description

A programme of work has been proposed between NHS Greater Glasgow & Clyde, Glasgow City Council, NRS and others. The aim of this work would be to enable a greater understanding of who is on the CHI population register but not included in the NRS population estimates and who might be included in the NRS population estimates who is not on the CHI population register.

Estimate of resource required

Significant. The project will start with NHS Greater Glasgow & Clyde but will have to be replicated for all health boards over time if this initial programme of work yields improved population estimates.

Feasibility

Subject to data controller approvals.