TAGRA –2014/15 to 2015/16 work plan

TAGRA(2014)05

# Introduction

This paper sets out TAGRA’s high level work plan between 2014/15 and 2015/16. TAGRA are asked to confirm that they would like the  developmental projects outlined below, to be undertaken between 2014/15-2015/16. This is in addition to a population only formula update in 2014/15. TAGRA have previously agreed that the MLC acute review would be undertaken under this work plan.

WORK PLAN

The following TAGRA work plan has been proposed for 2014/15-2015/16:

Previously agreed work

Review of acute costs

Review of MLC (acute care programme) (see also Annex A)

Review of population estimates (stage 2)

Annual NRAC formula run

Community Health Data

Highlands & Islands Travel Scheme

New work

Transfer of Prisoner healthcare

SAF formula review

The following tables outline the resource estimates required to undertake the programme of work, timescales and project leads. Note, the work plan excludes resourcing  required for  routine NRAC work, for example, answering Parliamentary Questions, briefing, ad hoc queries which occur throughout the year.

| Project | Estimate of Analytical Support Team resource required | Further information | Project timescales | Project lead | TAGRA representative | Progress – Green / Amber / Red | Main Risks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Population estimates (Phase 2) | 6 days | National Records of Scotland, NHS GG&C, City of Glasgow Council, NHS CR, ISD Scotland data linkage team | 2012/13-2013/14 | Kirsty MacLachlan | Paul James / Linda De Caestecker | GREEN |  |
| Acute costs review | XX days |  | Feb 2014 - | Roger Black | Roger Black | GREEN | Subgroup members availability PLICS methodology – timings of it’s introduction |
| NRAC 2015/16 formula run | 15 days | Population only update | May – August 2014 | Roger Black | Roger Black | GREEN |  |
| Highlands & Islands Travel Scheme | 10 days |  | XX | Angela Campbell | Angela Campbell | GREEN |  |
| Transfer of Prisoner healthcare | 30 days |  | November 2013 | Roger Black | Roger Black | GREEN |  |
| Morbidity & Life Circumstances (Acute) | 24 months |  | Feb 2014 –Spring 2016 | Karen Facey | Karen Facey | GREEN | AST Staff resources Assumes the analysis does not throw up unexpected findings which merit further investigation. Acute costing review timescales will impact on MLC Acute review |
| Community Health Data | 6 days |  | Dec 2013 – April 2015 (for first stage) | John Ross Scott | John Ross Scott, Karen Facey | GREEN | Data might not be available in all health boards within the timescales. Unknown data quality. |
| SAF Formula Review | Still to be scoped | The analytical work will be undertaken by the same members of the ISD NRAC team, and some of the ASD team. A further 1 or 2 people from ASD are likely to be involved in the work. Also input from PSD will be required. | Approx 2 years from August 2013 | Angela Campbell/ Lynda Nicholson | Angela Campbell/ Lynda Nicolson | GREEN | This project is yet to be scoped – must keep this manageable and focus on the key requirements of a revised SAF formula. |

Code to Risk:

Red – Significant risk to being delivered on time

Amber – Risk to elements of project not being delivered on time, or a small risk to the delivery of the project being late

Green – Project progressing to schedule

Scheduling of projects

RISKS TO DELIVERY

These projects represent TAGRA Analytical Support Team’s ambitions for the coming two years in addition to the annual formula update. There is a risk that they cannot be delivered due to resource constraints but by building the work plan over two years this means there is greater flexibility around when different work programmes can be taken forward.

Required resources

Some of these projects, by their nature, are potentially open ended. They can also be dependent on other pieces of work that are out with the control of the TAGRA team. For example, whilst the review of the acute costs is relatively well defined and a self-contained pieces of work, it is dependent on the IRF costing work becoming available for use in the formula and other applications. Projects such as the  review of the MLC acute adjustment and the population estimates project are potentially extremely lengthy pieces of work. It is difficult to specify the timescales and resources required to undertake this work thoroughly, as there is a risk that any initial review of the area identifies issues which are currently unknown, either requiring further detailed analysis or opening entirely new avenues of investigation.

This work plan contains an additional significant project, the SAF Formula review. The resources required to carry out this work are being found from within Health ASD and ISD teams, and some of this is additional to the current TAGRA support team, but most of the staff involved are the same people – this was one of the key reasons for bringing this work under the TAGRA oversight. It will continue to be a challenge to meet all the requirements of the projects set out in this work plan and will be the focus of continuous oversight by ISD and ASD senior management.

Other risks

The population estimates project in addition will involve data sharing and therefore several data controller approval stages. It is difficult to estimate accurately the time it will take to put all the permissions in place.

CONCLUSION

TAGRA members are invited to note the updated high level work plan. A further update will be available for August’s TAGRA meeting.

TAGRA Analytical Support Team (Health ASD & ISD)

May 2014

ANNEX A – High level outline of MLC Acute Care Programme Review

- Preparation of activity and cost data for the seven diagnostic groups

- Read Robertson Centre for Biostatistics report and other relevant materials

- Identification of potential indicators

- Review costing methodology

- Scope stability of activity and cost data and preferred size of analysis

- Initial test of data stability, agreed potential functional forms, age splits, 'medium' list of indicators, and preferred geographies

- Initial statistical results

- Agree short list of indicators, final functional form, age split and geography - initial assessment against core criteria

- Statistical results

- Assessment against TAGRA core criteria

- Analysis of final preferred set of options

- Assessment against TAGRA core criteria

- Draft Final Report

- Draft Health Inequalities IA

- Present recommendations to TAGRA

ANNEX B – Population estimates project (Stage 2)

# Background

## A review and comparison of existing datasets by NRS (National Records of Scotland) has been carried out as part of phase 1 of the project. It concluded that there is no indication that there are any problems with the MYEs (Mid Year Estimates). To understand the differences further, it is proposed that a data-linkage exercise be pursued in order to create a population estimate through record linkage.

## This phase of the project has been set up to continue to investigate the possible differences in population estimates between different data sources across Scotland, with a view to understanding the differences. This extends the work carried out in phase 1.

## This project will now form a work stream within the wider Beyond 2011 programme but will still require working closely with our partners in the NHS and Glasgow City Council.

## The Beyond 2011 Programme was established by the National Records of Scotland (NRS) in September 2011 to explore the future provision of population and socio-demographic statistics in Scotland. It aims to provide a recommendation to Ministers in early 2015.

## The programme aims to investigate a range of possible solutions for collecting census type information in 2021 and beyond. These solutions include the possibility of using administrative sources or developing a more cost-effective and efficient census design or some combination of these approaches.

# Project objectives

## The primary objectives for this project are:

- to progress the research on the administrative models for Beyond 2011 programme, including the signs-of-life work.

- to review and document the different CHI (Community Health Index) databases and to understand how these are used across Scotland and how they are updated.

7

- to provide a better understanding of the differences between population estimates in Scotland calculated by NRS (the Census and the Mid-Year-Estimates) and estimates derived from administrative data sources, such as the CHI, NHSCR (NHS Central Register), Local Authority (LA) data, etc.  To then use this information to determine if it is possible to use administrative data sources to contribute to population statistics.

- to identify any potential differences in the population estimates for particular geographical areas or subsets of the population, with the intention of documenting, explaining and assessing the implications of these differences where possible.

# Project timescales

The timing of the project will depend on the availability of datasets and resources to carry out the linkages.