TAGRA Acute MLC subgroup – 10th meeting, 18th August 2015 		TAMLC31

Outstanding Actions/Matters arising from meetings: 12th March 2014 – 9th June 2015

| Meeting date | Action | Status | Who |
| --- | --- | --- | --- |
| 9th June 2015 | AST to produce a simple methodology paper outlining the work to be done on unmet need, referring back to the NRAC report and technical addendum to ensure all areas of possible unmet need are re-investigated. | In progress | AST |
| 9th June 2015 | ISD members to meet with an NSS pharmacy advisor to discuss which drug types might be most related to additional need, particular for older ages, and how to best avoid rewarding inefficient prescribing. | Completed – outcome of conversation with ISD Pharmacy dvisor, Barry Melia is outlined in the Revised Potential Candidate Variables paper (TAMLC29). | AST |
| 9th June 2015 | AST to produce a further iteration of the potential candidate variables paper, with descriptions for variables where needed, and any further suggestions from meeting with pharmacy advisor. | Completed. | AST |
| 9th June 2015 | AST to check what mental health-related variable had been used by Bruce Guthrie and add to the potential candidate variables. |  |  |
| 9th June 2015 | AST to draft report outline for August meeting. | Completed | AST |
| 19th March 2015 | Agree timing of final update to DoFs in advance of the end of the group’s work | In progress | TR |
| 19th March 2015 | Circulate draft TAGRA paper to subgroup for feedback via email | Completed – Paper presented to TAGRA on 30th April 215 | DM/KF |
| 19th March 2015 | Remove SIMD from potential indicator variables table | Completed - Updated table included within TAMLC 29 | AST |
| 19th March 2015 | Verify analysis for 3 year intermediate zones and to seek an explanation for the differences in R-squared values between the two geography levels | Completed – included within Technical paper circulated to members on the geography decision | AST |
| 19th March 2015 | Subgroup to decide on geography and time span by email | Completed –Technical paper circulated to members to approve data zones as geography basis for the AMLC review | All subgroup members |
| 19th March 2015 | Produce initial exploratory analysis of diagnostic groupings | Planned for Jan-Mar 2016 as part of potential indicators/regression analysis | AST |
| 19th March 2015 | Invite equality leads to the August 2015 meeting | In progress | PC/DM |
| 19th March and 14th January 2015 | Age split regression analysis over 75 and over 65 | Completed – included within TAMLC 27 | AST |
| 14th January 2015 | Consult with appropriate clinicians on the age split when modelling the acute data | Ongoing – AST to speak to Prof Bruce Guthrie | AST |
| 2nd October 2014 | AST to continue to develop the analysis on unmet need based on the discussions of the group | Completed – included within TAMLC 28 | PK/PO/TR |
| 2nd October 2014 | Investigate any available data on high resource patients | Ongoing – data from IRF team being investigated through potential indicators work stream | AST |
| 2nd October 2014 | Consider drug classes/counts when looking at potential indicators of need | Ongoing – data from ISD being investigated through potential indicators work stream | AST |
| 2nd October 2014 | Investigate modelling used for HSMR | Ongoing | AST |
| 12th March 2014 | Draft summary of plans for sub-group work for Chairs and CEO updates. Action changed following TAGRA meeting in May to present to Chairs in person | Ongoing - Waiting to hear from Garry Coutts (Chairperson, NHS Highland) | KF/AST |