## Revised detailed work plan
At 11th April 2016
|  |  | Feb 2014 |  |  |  | Mar 2014 |  |  |  |  | Apr 2014 |  |  |  | May 2014 |  |  |  | Jun 2014 |  |  |  |  | Jul 2014 |  |  |  | Aug 2014 |  |  |  | Sept 2014 |  |  |  |  | Oct 2014 |  |  |  | Nov 2014 |  |  |  | Dec 2014 |  |  |  |  | Jan 2015 |  |  |  | Feb 2015 |  |  |  | Mar 2015 |  |  |  |  | Apr 2015 |  |  |  | May 2015 |  |  |  | Jun 2015 |  |  |  |  | Jul 2015 |  |  |  | Aug 2015 |  |  |  |  | Sep 2015 |  |  |  | Oct 2015 |  |  |  | Nov 2015 |  |  |  |  | Dec 2015 |  |  |  | Jan 2016 |  |  |  | Feb 2016 |  |  |  |  | March 2016 |  |  |  | April 2016 |  |  |  | May 2016 |  |  |  |  | June 2016 |  |  |  | July 2016 |  |  |  | August 2016 |  |  |  |  | September 2016 |  |  |  | October 2016 |  |  |  |  | November 2016 |  |  |  | December 2016
Week | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152
Date | time axis 2014-01-20 to 2016-12-26
Read GG&C report and relevant materials | 2014-02-03: AMLC Subgroup meeting (4th February 2014); 2014-03-10: AMLC Subgroup meeting (12th March 2014); 2014-03-31: AMLC Subgroup meeting (1st April 2014); 2014-05-12: AMLC Subgroup meeting (14th May 2014); 2014-05-26: TAGRA (29th May 2014); 2014-08-25: TAGRA (28th August 2014) & Acute MLC Subgroup (26th August); 2014-10-06: AMLC Subgroup meeting 2nd October 2014; 2014-12-15: TAGRA (15th December 2014); 2015-01-12: AMLC Subgroup meeting 15th January 2015; 2015-03-16: AMLC Subgroup meeting 19th March 2015; 2015-04-27: TAGRA (30th April 2015); 2015-06-08: AMLC Subgroup meeting 9th June 2015; 2015-08-10: AMLC Subgroup meeting 18th August 2015; 2015-08-24: TAGRA (27th August 2015); 2016-01-11: AMLC Subgroup meeting (20th January 2016); 2016-02-08: TAGRA (9th February 2016); 2016-03-21: AMLC Subgroup meeting (15 March 2016); 2016-05-16: AMLC Subgroup meeting (5 May 2016); 2016-08-08: AMLC Subgroup August meeting (tbc); 2016-08-29: TAGRA (25th August 2016); 2016-12-12: TAGRA (tbc)
Review of costing methodology (Current NRAC method V PLICS) | bar: 2014-01-20 to 2014-01-27; 2014-02-10 to 2014-03-03; 2014-03-17 to 2014-03-24; 2014-04-07 to 2014-05-05; 2014-05-19
Develop initial list of potential candidate variables | bar: 2014-01-20 to 2014-01-27; 2014-02-10 to 2014-03-03; 2014-03-17 to 2014-03-24; 2014-04-07 to 2014-05-05
Proposal paper to subgroup on functional form | bar: 2014-01-20 to 2014-01-27; 2014-04-21 to 2014-05-05
Recommendation on costing methodology to TAGRA | bar: 2014-01-20 to 2014-01-27; 2014-04-28 to 2014-05-05; 2014-05-19
Health Inequalities Impact Assessment - Scoping | bar: 2014-01-20 to 2014-01-27; 2014-04-28 to 2014-05-05; 2014-05-19; 2014-06-02 to 2014-08-18; 2014-09-01 to 2014-09-29
Review of casemix adjustment methodology | bar: 2014-01-20 to 2014-01-27; 2014-05-19; 2014-06-02 to 2014-08-18
Report to subgroup | bar: 2014-08-18
Report toTAGRA on casemix adjustment methodology | bar: 2014-08-18
Further analysis on casemix adjustment | bar: 2014-09-01 to 2014-09-29
Presentation on multimorbidity - Professor Bruce Guthrie | bar: 2014-09-29
Unmet need - scoping of analysis previously carried out and what is currently done in England | bar: 2014-09-01 to 2014-09-29
Report to subgroup and make recommendation on casemix adjustment | bar: 2014-09-29
Update toTAGRA on casemix adjustment methodology | bar: 2014-12-08
Investigate impact of redrawn Data Zones/Intermediate Zones on potential indicators of need and on timescale of Acute MLC review | bar: 2014-10-13 to 2014-12-08; 2014-12-22 to 2015-01-05
Initial analysis looking at age splits (age/sex cost curves) by diagnostic group | bar: 2014-10-13 to 2014-12-08; 2014-12-22 to 2015-01-05
Report to subgroup - make recommendation on whether to conduct Acute MLC review at redrawn geography | bar: 2015-01-05
Update current needs index with up-to-date LLTI (2011 Census) and SMR data | bar: 2015-01-19 to 2015-02-09
SIMD analysis - investigate the explanatory power of SIMD 2012 using current reference model | bar: 2015-02-16 to 2015-03-09
Geography and Time Span analysis - Data Zones/Intermediate Zones;1 year/3 years | bar: 2015-02-16 to 2015-03-09
Develop medium list of potential indicators | bar: 2015-02-16 to 2015-03-09
Report to subgroup - agree geography and time span; exclusion of SIMD from potential indicators | bar: 2015-03-09
Update to TAGRA | bar: 2015-04-20
Additional age split analysis; unmet need analysis | bar: 2015-03-23 to 2015-04-20; 2015-05-04 to 2015-06-01
Report to subgroup - agree next steps for age split and unmet need analysis | bar: 2015-06-01
Health Inequalities Impact Assessment - Prioritisation | bar: 2015-01-19 to 2015-03-09; 2015-03-23 to 2015-04-20; 2015-05-04 to 2015-06-01; 2015-06-15 to 2015-08-03
Prepare all available potential indicators at new data zones (note population data not available until August 2015) | bar: 2015-05-04 to 2015-06-01; 2015-06-15 to 2015-08-03
Investigate all other data sources e.g. Drug Counts, High Resource Individuals, Mental Health Data | bar: 2015-05-04 to 2015-06-01; 2015-06-15 to 2015-08-03
Develop final set of potential indicators available at redrawn Data Zones | bar: 2015-05-04 to 2015-06-01; 2015-06-15 to 2015-08-03
Prepare activity and costs data at redrawn Data Zones (3 years) | bar: 2015-05-04 to 2015-06-01; 2015-06-15 to 2015-08-03
Prepare for Health Inequalities Leads meeting | bar: 2015-05-04 to 2015-06-01; 2015-06-15 to 2015-08-03
Report to subgroup - present to Health Inequalities Leads | bar: 2015-08-03
Recalculate cost ratios at redrawn Data Zones (3 years) | bar: 2015-08-31 to 2015-11-16
Calculate all potential indicators at new data zones (3 years) | bar: 2015-08-31 to 2015-11-16
Outliers check at redrawn Data Zones (3 years) using current reference model | bar: 2015-08-31 to 2015-11-16
Health Inequalities Impact Assessment - Appraisal | bar: 2015-08-31 to 2016-01-04; 2016-01-18 to 2016-02-01; 2016-02-22 to 2016-03-14; 2016-03-28
Supply variables analysis to select supply model | bar: 2015-11-23 to 2016-01-04
Inter-correlations analysis to eliminate near-duplicate variables | bar: 2015-11-23 to 2016-01-04
Report to subgroup - Outliers analysis, Supply model, Inter-correlations analysis and agree list of retained variables | bar: 2016-01-04
Report to TAGRA | bar: 2016-02-01
First draft of Report | 2016-04-18: AMLC Subgroup meeting (15 April 2016); 2016-05-09: AMLC Subgroup meeting (5 May 2016); 2016-06-06: AMLC subgroup 6th June meeting; 2016-07-18: AMLC Subgroup 21st July meeting
Factor analysis and stepwise regressions | bar: 2016-01-18 to 2016-02-01; 2016-02-15 to 2016-03-14; 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18
Multiple regression using restricted variable set and analysis of coefficients | bar: 2016-01-18 to 2016-02-01; 2016-02-15 to 2016-03-14; 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18
Report to subgroup - Summarise statistical results and agree final index options | bar: 2016-03-14; 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18
Further analysis on final index options required. | bar: 2016-03-28 to 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18
First draft of report sent round sub-group | bar: 2016-03-28 to 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18
Report to subgroup - Summarise statistical results and agree final index | bar: 2016-04-11 to 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18
Analysis of final preferred set of options for new Acute Index | bar: 2016-04-18 to 2016-05-09; 2016-06-06; 2016-07-18
Test new Acute Index across urban rural categories and age groups | bar: 2016-04-18 to 2016-05-09; 2016-06-06; 2016-07-18
Second draft of Report | bar: 2016-04-18 to 2016-05-09; 2016-06-06; 2016-07-18
Report to subgroup - Summarise analysis of new index, urban rural categories and age groups | bar: 2016-04-18; 2016-05-02 to 2016-05-09; 2016-06-06; 2016-07-18
Unmet need analysis based on new Acute Index | bar: 2016-04-18; 2016-05-09 to 2016-06-06; 2016-07-18
HIIA appraisal | bar: 2016-04-18; 2016-05-09 to 2016-06-06; 2016-07-18
Third / forth drafts of report | bar: 2016-04-18; 2016-05-09 to 2016-06-06; 2016-07-18
Report to subgroup - Unmet need analysis and HIIA | bar: 2016-04-18; 2016-05-09; 2016-05-30 to 2016-06-06; 2016-07-18
Final Report | bar: 2016-04-18; 2016-05-09; 2016-06-06 to 2016-07-18
Health Inequalities Impact Assessment - Recommendations | bar: 2016-04-18; 2016-05-09; 2016-06-06 to 2016-07-18
Report to subgroup - Final Report | bar: 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18 to 2016-08-01
Present formula recommendations to TAGRA | bar: 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18; 2016-08-22
Formula impact assessment | bar: 2016-04-18; 2016-05-09; 2016-06-06; 2016-07-18; 2016-09-05 to 2016-12-05
Present report on impact assessment toTAGRA for approval and sub group for info. | bar: 2016-06-06; 2016-07-18; 2016-12-05

## Daily work plan
| Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
 | time axis 2016-04-25 to 2016-09-20
Agree final index | bar: 2016-04-25 to 2016-04-28
AST meeting | bar: 2016-04-29
Draft report to sub-group | bar: 2016-04-29
Paper on new model / age split / UR sent to sub-group | bar: 2016-04-29 to 2016-05-03
Review paper on new model / age split / UR | bar: 2016-05-04
Sub group meeting (5/5 10 AM, Gyle Square) | bar: 2016-05-05
Unmet need analysis | bar: 2016-05-06 to 2016-05-30
Paper to sub group on unmet need analysis | bar: 2016-05-30 to 2016-06-05
Sub group meeting 6 June | bar: 2016-06-06
Draft reports to sub-group for comment | bar: 2016-06-07 to 2016-07-31
Sub group meeting - 21 July | bar: 2016-07-21

## Daily work plan 2
|  | Agree final index | AST meeting | Draft report to sub-group | Paper on new model / age split / UR sent to sub-group | Review paper on new model / age split / UR | Sub group meeting 5th May | Paper to sub group on ethnicity variable (TAMLC53) | Final decision on index | Unmet need analysis | Paper to sub group on unmet need analysis so far | Draft reports to sub-group for comment | Sub group meeting 6 June | Finalise unmet need analysis | Next draft of TAGRA report | Send final unmet need analysis to sub group | Sub group meeting - 21 July
Mon | 2016-04-25
Tue | 2016-04-26
Wed | 2016-04-27
Thu | 2016-04-28
Fri | 2016-04-29
Sat | 2016-04-30
Sun | 2016-05-01
Mon | 2016-05-02
Tue | 2016-05-03
Wed | 2016-05-04
Thu | 2016-05-05
Fri | 2016-05-06
Sat | 2016-05-07
Sun | 2016-05-08
Mon | 2016-05-09
Tue | 2016-05-10
Wed | 2016-05-11
Thu | 2016-05-12
Fri | 2016-05-13
Sat | 2016-05-14
Sun | 2016-05-15
Mon | 2016-05-16
Tue | 2016-05-17
Wed | 2016-05-18
Thu | 2016-05-19
Fri | 2016-05-20
Sat | 2016-05-21
Sun | 2016-05-22
Mon | 2016-05-23
Tue | 2016-05-24
Wed | 2016-05-25
Thu | 2016-05-26
Fri | 2016-05-27
Sat | 2016-05-28
Sun | 2016-05-29
Mon | 2016-05-30
Tue | 2016-05-31
Wed | 2016-06-01
Thu | 2016-06-02
Fri | 2016-06-03
Sat | 2016-06-04
Sun | 2016-06-05
Mon | 2016-06-06
Tue | 2016-06-07
Wed | 2016-06-08
Thu | 2016-06-09
Fri | 2016-06-10
Sat | 2016-06-11
Sun | 2016-06-12
Mon | 2016-06-13
Tue | 2016-06-14
Wed | 2016-06-15
Thu | 2016-06-16
Fri | 2016-06-17
Sat | 2016-06-18
Sun | 2016-06-19
Mon | 2016-06-20
Tue | 2016-06-21
Wed | 2016-06-22
Thu | 2016-06-23
Fri | 2016-06-24
Sat | 2016-06-25
Sun | 2016-06-26
Mon | 2016-06-27
Tue | 2016-06-28
Wed | 2016-06-29
Thu | 2016-06-30
Fri | 2016-07-01
Sat | 2016-07-02
Sun | 2016-07-03
Mon | 2016-07-04
Tue | 2016-07-05
Wed | 2016-07-06
Thu | 2016-07-07
Fri | 2016-07-08
Sat | 2016-07-09
Sun | 2016-07-10
Mon | 2016-07-11
Tue | 2016-07-12
Wed | 2016-07-13
Thu | 2016-07-14
Fri | 2016-07-15
Sat | 2016-07-16
Sun | 2016-07-17
Mon | 2016-07-18
Tue | 2016-07-19
Wed | 2016-07-20
Thu | 2016-07-21
Fri | 2016-07-22
Sat | 2016-07-23
Sun | 2016-07-24
Mon | 2016-07-25
Tue | 2016-07-26
Wed | 2016-07-27
Thu | 2016-07-28
Fri | 2016-07-29
Sat | 2016-07-30
Sun | 2016-07-31
Mon | 2016-08-01
Tue | 2016-08-02
Wed | 2016-08-03
Thu | 2016-08-04
Fri | 2016-08-05
Sat | 2016-08-06
Sun | 2016-08-07
Mon | 2016-08-08
Tue | 2016-08-09
Wed | 2016-08-10
Thu | 2016-08-11
Fri | 2016-08-12
Sat | 2016-08-13
Sun | 2016-08-14
Mon | 2016-08-15
Tue | 2016-08-16
Wed | 2016-08-17
Thu | 2016-08-18
Fri | 2016-08-19
Sat | 2016-08-20
Sun | 2016-08-21
Mon | 2016-08-22
Tue | 2016-08-23
Wed | 2016-08-24
Thu | 2016-08-25
Fri | 2016-08-26
Sat | 2016-08-27
Sun | 2016-08-28
Mon | 2016-08-29
Tue | 2016-08-30
Wed | 2016-08-31
Thu | 2016-09-01
Fri | 2016-09-02
Sat | 2016-09-03
Sun | 2016-09-04
Mon | 2016-09-05
Tue | 2016-09-06
Wed | 2016-09-07
Thu | 2016-09-08
Fri | 2016-09-09
Sat | 2016-09-10
Sun | 2016-09-11
Mon | 2016-09-12
Tue | 2016-09-13
Wed | 2016-09-14
Thu | 2016-09-15
Fri | 2016-09-16
Sat | 2016-09-17
Sun | 2016-09-18
Mon | 2016-09-19
Tue | 2016-09-20

## Daily work plan 3
Dates
Task | Start | End
AST meeting | 2016-04-29 | 2016-04-29
Draft report to sub-group | 2016-04-29 | 2016-04-29
Paper on new model / age split / UR sent to sub-group | 2016-04-29 | 2016-05-05
Review paper on new model / age split / UR | 2016-04-29 | 2016-05-05
Sub group meeting 5th May | 2016-05-05 | 2016-05-05
Paper to sub group on ethnicity variable (TAMLC53) | 2016-05-11 | 2016-05-18
Final decision on index | 2016-05-18 | 2016-05-18
Unmet need analysis | 2016-05-05 | 2016-05-30
AST paper to AST
AST meeting
Paper to sub group on unmet need analysis so far | 2016-05-30 | 2016-06-06
Draft reports to sub-group for comment | 2016-05-30 | 2016-06-06
Sub group meeting 6 June - Finalise unmet need analysis and decision made on any adjustment | 2016-06-06 | 2016-06-06
Next draft of TAGRA report | 2016-07-14 | 2016-07-14
Send final unmet need analysis to sub group | 2016-07-14 | 2016-07-21
Sub group meeting - 21 July
TAGRA meeting 23rd Aug