Outstanding Actions/Matters arising from meetings: 12th March 2014 – 2nd October 2014

| Meeting date | Action | Status | Who |
| --- | --- | --- | --- |
| 2nd October 2014 | Arrange conference call with MS to discuss the unmet need work. | Ongoing – Meeting is currently being arranged for January/February 2015. | KF |
| 2nd October 2014 | PO to continue to develop the analysis on unmet need based on the discussions of the group and talk to the SPARRA team. | Ongoing – verbal update to be provided on 14th January and any analysis will be presented at future subgroup meeting. | PO |
| 2nd October 2014 | Investigate any available data on high resource patients. | Progress included within TAMLC 20. | AST and DG, AD |
| 2nd October 2014 | Consider drug classes/counts when looking at potential indicators of need. | Progress included within TAMLC 20. | AST |
| 2nd October 2014 | Investigate modelling used for HSMR. | Ongoing. | AST |
| 2nd October 2014 | Provide verbal update to TAGRA on the case-mix adjustment recommendation. | Completed. | KF |
| 2nd October 2014 | Liaise with colleagues on concrete timescales for completion of the new datazones and assess the impact on the Acute MLC work plan. | Progress included within TAMLC 20. | AST |
| 2nd October 2014 | Consult with appropriate clinicians on the age split when modelling the acute data. | Progress included within TAMLC 19. | AST |
| 12th March 2014 | Draft summary of plans for sub-group work for Chairs and CEO updates. Action changed following TAGRA meeting in May to present to Chairs in person. | Ongoing - Waiting to hear from Garry Coutts (Chairperson, NHS Highland) | AST |