TAGRA Acute MLC subgroup - 9th meeting, 9th June 2015 			TAMLC 26

Outstanding Actions/Matters arising from meetings: 12th March 2014 – 19th March 2015

| Meeting date | Action | Status | Who |
| --- | --- | --- | --- |
| 19th March 2015 | Agree timing of final update to DoFs in advance of the end of the group’s work | In progress | TR |
| 19th March 2015 | Circulate draft TAGRA paper to subgroup for feedback via email | Completed – Paper presented to TAGRA on 30th April 215 | DM/KF |
| 19th March 2015 | Remove SIMD from potential indicator variables table | Completed - Updated table included within TAMLC 29 | AST |
| 19th March 2015 | Verify analysis for 3 year intermediate zones and to seek an explanation for the differences in R-squared values between the two geography levels | Completed – included within Technical paper circulated to members on the geography decision | AST |
| 19th March 2015 | Subgroup to decide on geography and time span by email | Completed –Technical paper circulated to members to approve data zones as geography basis for the AMLC review | All subgroup members |
| 19th March 2015 | Produce initial exploratory analysis of diagnostic groupings | Planned for Jan-Mar 2016 as part of potential indicators/regression analysis | AST |
| 19th March 2015 | Invite equality leads to the August 2015 meeting | In progress | PC/DM |
| 19th March and 14th January 2015 | Age split regression analysis over 75 and over 65 | Completed – included within TAMLC 27 | AST |
| 14th January 2015 | Consult with appropriate clinicians on the age split when modelling the acute data | Ongoing – AST to speak to Prof Bruce Guthrie | AST |
| 2nd October 2014 | AST to continue to develop the analysis on unmet need based on the discussions of the group | Completed – included within TAMLC 28 | PK/PO/TR |
| 2nd October 2014 | Investigate any available data on high resource patients | Ongoing – data from IRF team being investigated through potential indicators work stream | AST |
| 2nd October 2014 | Consider drug classes/counts when looking at potential indicators of need | Ongoing – data from ISD being investigated through potential indicators work stream | AST |
| 2nd October 2014 | Investigate modelling used for HSMR | Ongoing | AST |
| 12th March 2014 | Draft summary of plans for sub-group work for Chairs and CEO updates. Action changed following TAGRA meeting in May to present to Chairs in person | Ongoing - Waiting to hear from Garry Coutts (Chairperson, NHS Highland) | KF/AST |