TAGRA –2013/14 to 2014/15 work plan

TAGRA(2013)02

# Introduction

- This paper sets out TAGRA’s high level work plan between 2013/14 and 2014/15. TAGRA are asked to confirm that they would like the  developmental projects outlined below, to be undertaken between 2013/14-2014/15. This is in addition to the full NRAC formula run in 2013/14 and a population only formula update in 2014/15.

- PROPOSED WORK PLAN

- The following TAGRA work plan has been proposed for 2013/14-2014/15:

  - Review of acute costs

  - Review of MLC (acute care programme) (see also Annex A)

  - Review of population estimates

  - Transfer of Prisoner healthcare

  - Highlands & Islands Travel Scheme

  - Annual NRAC formula run

- The following tables outline the resource estimates required to undertake the programme of work, timescales and project leads. Note, the work plan excludes resourcing  required for  routine NRAC work, for example, answering Parliamentary Questions, briefing, ad hoc queries which occur throughout the year.

| - Project | - Estimate of Analytical Support Team resource required | - Estimate of wider resources required | - Project - timescales | - Project lead | - TAGRA representative | - Progress – - Green / - Amber / Red | - AST Risks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Population estimates (Phase 1) | - 6 days | - National Records of Scotland, NHS GG&C, City of Glasgow Council, NHS CR, ISD Scotland data linkage team | - 2012/13-2013/14 | - Kirsty MacLachlan | - Paul James / Linda De Caestecker | - GREEN |  |
| - Acute costs review | - 60 days |  | - April - July 2013 | - Roger Black | - Roger Black | - GREEN |  |
| - NRAC 2014/15 formula run | - 45 days |  | - May - September 2013 | - Roger Black | - Roger Black | - GREEN | - Publication of population estimates delay |
| - Highlands & Islands Travel Scheme | - 10 days |  | - October 2013 | - Angela Campbell | - Angela Campbell | GREEN |  |
| - Transfer of Prisoner healthcare | - 30 days |  | - November 2013 | - Roger Black | - Roger Black | GREEN |  |
| - Morbidity & Life Circumstances (Acute) | - 16 months |  | - November 2013 – Spring 2015 | - TBC | - TBC | - GREEN | - AST Staff resources - Assumes the analysis does not throw up unexpected findings which merit further investigation. |
| - NRAC 2015/16 formula run | - 15 days |  | - May-August 2014 | - Roger Black | - Roger Black | - GREEN |  |

- Code to Risk:

- Red – Significant risk to being delivered on time

- Amber – Risk to elements of project not being delivered on time, or a small risk to the delivery of the project being late

- Green – Project progressing to schedule

- Scheduling of projects

- RISKS TO DELIVERY

- These projects represent TAGRA Analytical Support Team’s ambitions for the coming two years in addition to the annual formula update. There is a risk that they cannot be delivered due to resource constraints but by building the work plan over two years means there is greater flexibility around when different work programmes can be taken forward.

- Required resources

- Some of these projects, by their nature, are potentially open ended. Whilst the review of the acute costs is relatively well defined and a self-contained pieces of work, any review of the MLC acute adjustment and the population estimates project, are potentially extremely lengthy pieces of work. It is difficult to specify the timescales and resources required to undertake this work thoroughly, as there is a risk that any initial review of the area identifies issues which are currently unknown, either requiring further detailed analysis or opening entirely new avenues of investigation.

- Other risks

- The population estimates project in addition will involve data sharing and therefore several data controller approval stages. It is difficult to estimate accurately the time it will take to put all the permissions in place.

- CONCLUSION

- TAGRA members are invited to agree the high level work plan. A further update will be available for August’s TAGRA meeting.

TAGRA Analytical Support Team (Health ASD & ISD)

April 2013

ANNEX A – High level outline of MLC Acute Care Programme Review

- Preparation of activity and cost data for the seven diagnostic groups

- Read Robertson Centre for Biostatistics report and other relevant materials

- Identification of potential indicators

- Scope stability of activity and cost data and preferred size of analysis

- Initial test of data stability, agreed potential functional forms, age splits, 'medium' list of indicators, and preferred geographies

- Initial statistical results

- Agree short list of indicators, final functional form, age split and geography - initial assessment against core criteria

- Statistical results

- Assessment against TAGRA core criteria

- Analysis of final preferred set of options

- Assessment against TAGRA core criteria

- Draft Final Report

- Present recommendations to TAGRA